
**MODULE 2: CALENDARS AND SCHEDULING**

***Exercise 1. Changing Working Time***


* **Schedule the project from a Project Start Date of 1 July 2024**
* **Choose an overall project calendar of Standard**

****


* **The office will shut down for 2 weeks in the summer. Use the Change Working Time dialog**

**box to create an Exception called "Summer Shutdown" and make the first 14 days of August**

**nonworking time**


****

* **Display the Project Information**

****

**Exercise 2. Changing Working Time**


* **Schedule it to start on 1 Dec 2024. The project will be based upon the Standard calendar**

****

* **Go to the Change Working Time dialog box and create an Exception to the Standard calendar**


**called "Xmas Bank Holidays". This needs to make 25 and 26 December 2024 into nonworking**


**time.**

****


* **Use the Work Weeks tab to change the Standard calendar's default working week. This**


**project's standard working time is:**

* + 08:30 to 17:30 Monday to Thursday (no lunch break)****
  + 08:30 to 16:00 on Fridays (no lunch break)


****

* + Add a new Work Week to the Standard calendar named "Xmas Slowdown". Use this to model a 12:30 finish on every weekday from 15 to 31 December 2024.

****


****

* **Display the Project Information.**

****

**Exercise 3. Part Time - creating new calendar**


* **Schedule it to start on 11 May 2024. This project should be based upon the Standard calendar.**

****


* **A part-time worker will be used on this project. Go to the Change Working Time dialog box**

**and create a new copy of the Standard calendar, calling it "Part Timer".**


* **Update the working time of your new calendar so that:**
  + **Mondays to Fridays are nonworking time**

****

* + **The remaining 2 weekdays have working time of 10:00 to 15:00 (with no breaks)**

****


* **The part timer has also booked a holiday to US from 2 to 11 September. Create an Exception to their calendar with a sensible name and model these days as nonworking**

****


* **Although the overall project will be based upon the Standard calendar (as per the Project**

**Information dialog box), feel free to format the Gantt Chart to show the nonworking time for**

**new Part Timer calendar.**

****

**Display the Project Information.**

****

**Exercise 4. Changing Working Time**

* **Open project file Ex6 (Module 1), Use the Project Information dialog box to schedule it to start on Nov 1st of next year.**